{"text_format":"3","workbook":"xlsx","n_sheets":1,"sheets":["Sheet1"],"read":"whole","date_system":"1900"}

{"sheet":"Sheet1","index":0,"n_rows":33,"n_cols":7,"rows_kept":33,"merged":[[0,0,0,6],[2,0,2,6],[14,0,14,6],[20,0,20,6],[22,3,31,3],[32,0,32,1]]}
["2022年中央财政衔接推进乡村振兴补助资金 （巩固拓展脱贫攻坚成果和乡村振兴任务） 安排计划表"]
[{"$nulls":4},"单位：万元"]
["一、8 个行政村村道硬底化，共计2830万元。"]
["序号","镇（村）名","安排资金","资金使用计划（即建设规模和工程量）","用       途","详细建设地点（细到自然村）","各建设点资金分配"]
[1,"上英镇浮头村",950,"完成浮头村（巷）道硬底化，巷道硬底化11880平方，盖石板5369平方，铺设透水砖3600平方，排污管22323米：雨水沟15674米，污水处理池1座","村（巷）道硬底化","浮头村",950]
[2,"东海镇上海村",390,"计划改造硬化大小村道巷道约38道，硬化面积约1.7万平方米。","村（巷）道硬底化","上海村",390]
[3,"河东镇青山村",400,"主要建设内容为硬底化约15000平方米，污水管网建设约5000米。","村（巷）道硬底化","青山村燕东自然村、              青山村芸头自然村","燕东自然村150万元，\n芸头自然村250万元。"]
[4,"桥冲镇溪碧村",400,"一、陆丰市桥冲镇溪碧村委文厝老村巷道硬底化工程：1、巷道硬底化，长度为3662米，平均宽度为2米，厚度为12公分混凝土及10公分碎石垫层；\n2、巷道排水沟，长度为2500m，新修砖砌排水沟及盖板；                                          二、陆丰市桥冲镇溪碧村委文厝新村巷道硬底化工程：1、巷道硬底化，长度为2680米，平均宽度为2米，厚度为12公分混凝土及10公分碎石垫层；\n2、巷道排水沟，长度为2000m，新修砖砌排水沟及盖板；                                          三、1、巷道硬底化，长度为350米，宽度为5米，厚度为20公分混凝土及18公分碎石垫层；","村（巷）道硬底化","委文厝老村、文厝新村、张厝村","文厝老村196万元；  文厝新村152万元； 张厝村52万元"]
[5,"甲西镇博社村",100,"项目位于博社村三村四村横巷，总长度约2384米，平均宽度2.4米，破除面积约6243米，硬化面积约6936平方米。","村（巷）道硬底化","博社村三村四村",100]
[6,"湖东镇深田湖村",200,"完善村内巷道硬化，12cm水泥混凝土路面7457.35㎡，20cm水泥混凝土路面4600.56㎡。","村（巷）道硬底化","深田湖村",200]
[7,"金厢镇下埔村",100,"1、清理杂草，建筑垃圾，面积2425㎡。\n2、拆除砼房，面积72.15㎡。\n3、雨水工程：新建落水井，44座，雨水检查井，9座；DN400双壁波纹管，195m, DN300双壁波纹管200m, DN200PVC管,565m。\n4、污水工程：新建入户井，18座，污水检查井，5座；DN400双壁波纹管，192m, DN300双壁波纹管200m, DN200双壁波纹管,184m。\n5、巷道硬底化工程：沥青道路（包括混凝土），面积1849.5㎡。","村（巷）道硬底化","下埔村",100]
[8,"西南镇青塘村",200,"青塘村委下辖自然村进行村内道路硬底化总建设里程长约5公里，宽2.5米。硬底化路面面积约13000平方米。","村（巷）道硬底化","以青塘村委云前村、桥东村、北门村为建设重点，松寨村、楼社村、乌石埔村、黄已寮村、朱厝寨村的部分道路硬底化。",200]
[9,"大安镇南溪村",90,"硬底化3200平方米、铺设250米DN600管道、220米DN300管道接雨水井。","村（巷）道硬底化","南溪村、新圩村、上寮村","南溪村约32万元、   新圩村约42万元、  上寮村约16万元。"]
[null,null,2830]
["二、4个镇村乡村风貌管控和农房微改造，共计470万元。"]
["序号","镇（村）名","安排资金","资金使用计划（即建设规模和工程量）","用        途","详细建设地点（细到自然村）","各建设点资金分配"]
[1,"潭西镇",180,"粉刷房屋数量121栋，粉刷面面积23885㎡","示范带沿线乡村风貌管控和农房微改造","太平村、后底村、上埔村","上埔村180万元"]
[2,"河西镇",200,"广告牌1800平方、穿衣戴帽1600平方、外立面美化22000平方。","示范带沿线乡村风貌管控和农房微改造","湖田、莲塘、山下、前厝堂、龙厝、后坑","湖田45万、莲塘20万、山下50万、前厝堂15万、龙厝10万、后坑60万。"]
[3,"东海镇",40,"示范带沿线农房微改造约35间，面积约2000平方米。","示范带沿线乡村风貌管控和农房微改造","东海大道、新324沿线",40]
[4,"城东镇",50,"示范带沿线风貌提升工程，长度约10公里","示范带沿线乡村风貌管控和农房微改造","324国道沿线及广汕公路",50]
["三、10个共同富裕村规划提升，计200万元。"]
["序号","镇（村）名","安排资金","资金使用计划","用        途"]
[1,"上英镇浮头村",20,"统一由市自然资源局负责这10个村庄规划。","共同富裕村规划提升"]
[2,"东海镇乌坎村",20,null,"共同富裕村规划提升"]
[3,"东海镇上海村",20,null,"共同富裕村规划提升"]
[4,"河东镇青山村",20,null,"共同富裕村规划提升"]
[5,"桥冲镇溪碧村",20,null,"共同富裕村规划提升"]
[6,"甲西镇博社村",20,null,"共同富裕村规划提升"]
[7,"金厢镇下埔村",20,null,"共同富裕村规划提升"]
[8,"西南镇青塘村",20,null,"共同富裕村规划提升"]
[9,"大安镇南溪村",20,null,"共同富裕村规划提升"]
[10,"城东镇高美村",20,null,"共同富裕村规划提升"]
["资金总计",null,3500]